## Sheet1
TASK | Start Date | End Date | Duration | Duration Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Semester1
Step 1: Dataset Collection | 2021-10-13 | 2021-10-27 | 14 | Step 1: Dataset Collection | bar: Week 2 to Week 3
Video Recording | 2021-10-20 | 2021-10-21 | 1 | Dataset Design Report | bar: Week 2 to Week 6
Video & Audio Seperation | 2021-10-21 | 2021-10-22 | 1 | Video Recording | bar: Week 2
Dataset Design Report | 2021-10-27 | 2021-12-01 | 35 | Video & Audio Seperation | bar: Week 2
Step 2: Visual Data pre-processing | 2021-10-27 | 2021-11-10 | 14 | Step 2: Visual Data pre-processing | bar: Week 4 to Week 5
Video processing script | 2021-10-31 | 2021-11-05 | 5 | Video processing script | bar: Week 4 to Week 5
Video conversion to images | 2021-11-05 | 2021-11-09 | 4 | Video conversion to images | bar: Week 4 to Week 5
Visual data processing report | 2021-10-27 | 2021-12-07 | 41 | Visual data processing report | bar: Week 4 to Week 9
Step 3: Audio pre-processing | 2021-11-10 | 2021-11-24 | 14 | Step 3: Audio pre-processing | bar: Week 6 to Week 11
Installation of python speech features | 2021-11-11 | 2021-11-17 | 6 | Installation of python speech features | bar: Week 6 to Week 7
Extraction of MFCC | 2021-11-18 | 2021-11-23 | 5 | Extraction of MFCC | bar: Week 8 to Week 9
Audio pre-processing report | 2021-11-10 | 2022-01-01 | 52 | Audio pre-processing report | bar: Week 7 to Week 11
Step 4: Audio to image prediction network | 2021-11-24 | 2022-04-30 | 157 | Step 4: Audio to image prediction network
Pytorch installation | 2021-11-25 | 2021-11-26 | 1 | Pytorch installation
Pytorch dataset class creation for images | 2021-11-27 | 2022-02-23 | 88 | Pytorch dataset class creation for images
Design Model | 2022-02-24 | 2022-03-30 | 34 | Design Model
Training algorithm Development | 2022-03-31 | 2022-04-30 | 30 | Training algorithm Development
Step 5: Evaluation | 2021-11-24 | 2022-05-05 | 162 | Step 5: Evaluation
|  |  |  | Duration Task | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Semester 2
Step 1: Dataset Collection
Dataset Design Report
Video Recording
Video & Audio Seperation
Step 2: Visual Data pre-processing
Video processing script
Video conversion to images
Visual data processing report
Step 3: Audio pre-processing | bar: Week 12
Installation of python speech features
Extraction of MFCC
Audio pre-processing report | bar: Week 12
Step 4: Audio to image prediction network
Pytorch installation | bar: Week 13
Pytorch dataset class creation for images | bar: Week 13 to Week 15
Design Model | bar: Week 16 to Week 18
Training algorithm Development | bar: Week 17 to Week 22
Step 5: Evaluation | bar: Week 20 to Week 22